## Pipe SAP 31.07.2025
[8 empty] | 146 |  | 212
PIPE PROJECT STATUS | Last updated on 08/08/25 | [8 empty] | 118 | 122 | [17 empty] | Total Outflow till completion of Project
Name of Project | SAP code | Work Order Value including O&M | Capex Value | O&M Value | Material WO | Service WO | GST Diff to be Claimed, So order Value will change. Hence, Balance work &/or Outstnding figure - will get adjusted. | Total Billing Upto 31.07.2025 | % | Material up to 31.07.2025 | Services up to 31.07.2025 | Total Billing Q2 | Balance Work Rs. Wherever figure is minus, it is pending due to non-submission of final bill or claims are pending or GR entries are pending. | Gross collection as on Date (Gross RA Bill) | Net collection | % of RA Bill | O/s As on 31.07.2025 | % | o/s EMD | o/s SD | o/s Other | Total O/S as on 31.07.2025 | BG O/S as on 30.06.2025 | Our Claim Dispute - Legal Case | Project Status by Manager. |  | Collection Target in August -25 | Billing to be done includuing GST | Vendor Expenses/ Bills likely to be incurred | Labour/ Contractor due Paymnet as on 08/08/25 | Likely Matrial Purchase/ supply likely required for completion of project |  | Total outflow | Remarks | Sale in FY 25-26 | Collection 25-26
Balaghat | 20016583 | 38.681 |  |  |  |  | GST Diff Claim | 38.9275 | 100.6% | 16.6939 | 22.2336 | 0 | -0.24654 | 37.2175 | 33.0775 | 96.22% | 2.0657 | 5.34% | 0 | 1.7477 | 6.78e-05 | 3.8134 | 1.9341 |  | Completed. Follwing up for Handover & Final Bill |  | 1 | nil | 0.3 | 0.12 |  |  | 0.42 |  | nil | 3.81
JabalPur 24x7 O&M started on 1/4/25.. O&M 2.65 cr for 3 zones but one zone descope hence 1.76 cr OM for 5 yrs. 0.35 per year | 20021445 | 20.452 | 17.8 | 2.652 |  |  |  | 18.2072 | 89.02% | 9.4359 | 8.7712 | 0 | 2.2449 | 16.5118 | 15.1437 | 80.73% | 1.6523 | 8.079% | 0 | 0.70697 | 0 | 2.3592 | 0 |  | Capex completed. O&M Started from 1st April 2025. Following up for fianl bill & Completion Certificate of capex |  |  | nil | 0.3 |  | 0.35 |  | 0.65 |  | nil | 1.24
Total MP |  | 59.133 | 17.8 | 2.652 |  |  |  | 57.1347 |  | 26.1299 | 31.0048 | 0 | 1.9983 | 53.7292 | 48.2212 |  | 3.718 |  | 0 | 2.4546 | 6.78e-05 | 6.1727 | 1.9341 |  |  |  | 1 |  | 0.6 | 0.12 | 0.35 |  | 1.07 |  |  | 5.05
Bhusawal | 20019598 | 46.5 |  | 0 |  |  |  | 77.0344 | 165.7% | 28.4379 | 48.5965 | 0 | -30.5344 | 45.0078 | 40.7631 | 96.79% | 32.0422 | 68.91% | 0 | 1.8644 | 0 | 33.9066 | 0 | Claim filed for 79 Cr Court Case to be filed. | Project short closed |  | 0 | NIL | 2.63 | 0.004 |  |  | 2.634 |  | nil | 2.56
JMC | 20019869 | 211.0846 |  | 0 |  |  | GST Diff Claim-Collected Rs.5,37,42,784 | 211.0759 | 100% | 60.5536 | 150.5222 | 0 | 0.0087582 | 210.151 | 197.5075 | 99.56% | 1.006 | 0.4766% | 0 | 4.926 | 0 | 5.932 | 0 |  | Completed , Following up for SD release of 4.15 cr against Bg |  | 4.93 | NIL | 0.2 | 1.08 |  |  | 1.28 |  | 0 | 4.93
Total MH |  | 257.5846 | 0 | 0 |  |  |  | 288.1102 |  | 88.9915 | 199.1187 | 0 | -30.5256 | 255.1587 | 238.2705 |  | 33.0482 |  | 0 | 6.7904 | 0 | 39.8386 | 0 |  |  |  | 4.93 |  | 2.83 | 1.084 | 0 |  | 3.914 |  | 0 | 7.49
Bijapur 24x7 Will close @ 179.68 Cr including GST. This may reduce by 10 CR. (Excluding O & M - To start September 2025) GST Claim Difference submitted 4.41 Cr Funds are not available, to recover money, we may have to go to court. PE, Royalty & Hard Rock given is being recovered/ deducted, to recover the same, we have to go for Legal Case. | 20017531 | 207.4676 | 179.68 | 27.7876 |  |  |  | 179.4452 | 86.49% | 62.0774 | 117.3678 | 0 | 0.23483 | 141.363 | 129.4085 | 68.14% | 39.2303 | 18.91% | 0 | 2.5968 | 0 | 41.8272 | 13.2215 |  | Completed Commissining & balance HSC, Metering inn process | Request for EOT upto 31st Dec 24 submitted to AEE. | 13.5 | NIL | 6.65 | 1.88 | 0.9 |  | 9.43 | Chorinators 15 Number installation, SCADA Errection & Commissioning, HSC 15000 Numbers, Road Restoration, Testing & Commisioning. Complete all pending jobs by March 15th without fail and handover the job. Also take completion. The O&M must start from 1st April 2025. |  | 20
Bagalkot 24x7 GST Claim Difference is 2.47 Cr PE, Royalty & Hard Rock given is being recovered/ deducted, to recover the same, we have to go for Legal Case. | 20017532 | 56.74 | 50.3 | 6.4351 |  |  | GST Diff Claim 2.47 Cr | 52.7805 | 93.02% | 18.8179 | 33.9626 | 0 | -2.4756 | 35.8501 | 32.4053 | 63.18% | 17.5153 | 30.87% | 0 | 0.69731 | 0 | 18.2126 | 4.1302 |  | Completed O&M started, Final bill in process | Handing over formalities in process. |  | NIL | 2.65 | 0.6 |  |  | 3.25 |  |  | 12.23
Nippani Receiable= 400 Lakhs CMC will release 2 CR in August & then 2Cr will be released. | 20014724 | 29.16 | 23.66 | 5.5 |  |  |  | 30.4061 | 104.3% | 11.9839 | 18.4222 | 0 | -1.2461 | 26.7183 | 24.7828 | 91.63% | 3.388 | 11.62% | 0 | 0 | 0 | 3.388 | 0 |  | O&M Completed Bills Submitted | O&M Period ended on 31st March 25. Site handovered | 0 | NIL | 0.6 | 0.12 |  |  | 0.72 |  |  | 3.61
Gokak Follow up for Balance payment with CMC | 20013988 | 27.9 | 21.45 | 6.45 |  |  |  | 27.9036 | 100% | 12.013 | 15.8906 | 0 | -0.0035921 | 26.5386 | 23.9648 | 95.12% | 2.019 | 7.237% | 0 | 0.096673 | 0.12981 | 2.2455 | 0 |  | Completed. |  | 0 | NIL | 0.3 | 0.05 |  |  | 0.35 |  |  | 2.3
Total KA |  | 321.2676 | 275.09 | 46.1727 |  |  |  | 290.5354 |  | 104.8922 | 185.6431 | 0 | -3.4905 | 230.4701 | 210.5614 |  | 62.1527 |  | 0 | 3.3908 | 0.12981 | 65.6733 | 17.3517 |  |  |  | 13.5 | NIL | 10.2 | 2.65 | 0.9 |  | 13.75 |  | 0 | 38.14
PHE Yamunanagar- O&M going on. Will be completed on 23/5/27 | 20024063 | 20.07 | 19.6375 | 0.43251 |  |  |  | 19.7822 | 98.57% | 18.0674 | 1.7147 | 0 | 0.28783 | 19.8427 | 19.2248 | 98.87% | 0.062141 | 0.3096% | 0 | 0.0086502 | 0.0001442 | 0.070935 | 0 |  | Completed. O&M is going on |  | 0.5 | NIL |  | 0 |  |  | 0 |  |  | 0.085
PHE Rewari | 20019189 | 40.47 | 39.48 | 0.99 |  |  |  | 40.4349 | 99.91% | 36.9702 | 3.4647 | 0 | 0.035051 | 39.9827 | 38.6504 | 98.8% | 0.3908 | 0.9657% | 0 | 0 | 0 | 0.3908 | 0 |  | Completed. O&M completed & Handovered |  |  | NIL |  |  |  |  | 0 |  |  | 0.39
PHE Bawal | 20019190 | 7.2408 | 7.0598 | 0.18102 |  |  |  | 7.2092 | 99.56% | 6.078 | 1.1312 | 0 | 0.031664 | 7.2092 | 6.7673 | 99.56% | 0.016539 | 0.2284% | 0 | 0.33358 | 0 | 0.35012 | 0 |  | Complted & Handovered |  |  | NIL |  |  |  |  | 0 |  |  | 0.36
PHE Jind- O&M going on. Completed on 31/3/27 | 20024433 | 15.24 | 14.8438 | 0.39616 |  |  |  | 15.4218 | 101.2% | 12.7981 | 2.6237 | 0 | -0.18179 | 14.8412 | 14.3344 | 97.38% | 0.55104 | 3.616% | 0 | 0 | 0 | 0.55104 | 0 |  | Completed. O&M is going on |  |  | NIL |  |  |  |  | 0 |  |  | 0.0829
CHARKHI DADRI- O&M going on. Completed on 23/3/28 | 20025083 | 27.82 | 27.0321 | 0.78789 |  |  | GST Diff Claim | 31.9196 | 114.7% | 27.911 | 4.0086 | 0 | -4.8875 | 27.0367 | 26.1423 | 97.18% | 4.3152 | 15.51% | 0 | 0.65856 | 0 | 4.9737 | 0 | Insurance claim filed for 1.80 Cr | Completed. O&M is going on |  |  | NIL |  |  |  |  | 0 |  |  | 3.0825
PHE TOHANA Complted. NO O&M | 20026203 | 31.07 | 31.07 | 0 |  |  | GST Diff Claim | 33.8034 | 108.8% | 31.1741 | 2.6293 | 0 | -2.7334 | 31.0694 | 29.1607 | 100% | 2.7341 | 8.8% | 0 | 1.0559 | 0 | 3.7899 | 0 |  | Completed. No O&M |  | 0.9 | NIL |  |  |  |  | 0 |  |  | 3.24
PHED, HANSI Part of work reduced. GR - CN. NO O&M | 20031074 | 4.424 | 4.424 |  |  |  |  | 4.3306 | 97.89% | 4.3306 | 0 | 0 | 0.093348 | 3.3 | 2.8477 | 74.59% | 1.1529 |  | 0 | 0.31215 | 0 | 1.4651 | 0.65113 |  | Pipe line Work completed. Only valve installation & final connection work is balance. |  | 0 | NIL | 0.28 |  | 0.005 | Nut bolts, gasket | 0.285 |  | NIL | 5.3
Total HR |  | 146.3348 | 143.5472 | 2.7876 | 0 | 0 |  | 152.9017 |  | 137.3295 | 15.5722 | 0 | -7.3548 | 143.2818 | 137.1277 |  | 9.2227 |  | 0 | 2.3688 | 0.0001442 | 11.5916 | 0.65113 |  |  |  | 1.4 |  | 0.28 | 0 | 0.005 |  | 0.285 |  | 0 | 12.5404
Grand Total |  | 784.3201 | 436.4372 | 51.6123 | 0 | 0 |  | 788.6821 |  | 357.3432 | 431.3389 | 0 | -39.3726 | 682.6399 | 634.1807 |  | 108.1416 |  | 0 | 15.0046 | 0.13002 | 123.2762 | 19.9369 |  |  |  | 20.83 |  | 13.91 | 3.854 | 1.255 |  | 19.019 |  | 0 | 63.2204
Ongoing Pune project
Pune 24x7- Original WO Value 375.62 (333 Capex (Material + Service) + 42.64 O&M) including GST @ 12% One item PLB Duct removed. so WO has been revised. Revised WO Capex- 358.42 cr incl GST CAPEX - 290.89 Cr Capex - GST Diff (12 Vs 18%) - 14.66Cr Escalation Recieved -17.46 Cr Exclation to be Recieved approx- 27.41 Cr Arbitration 7.99 Recieved GST diff to be Received 14.66 Total WO Value - 358.42 Cr + O&M - 42.64 Cr Including GST @ 12% + GST Difference. | 20020916 | 401.0589 | 358.42 | 42.6389 | 212 | 146.42 | GST Diff Claim submitted for 5.37 Cr as of 11/8/2025 Further to be submitted alongwith every RA Bill. | 221.3761 | 55.2% | 94.3981 | 126.978 | 0 | 137.0439 | 114.7709 | 102.4592 | 28.62% | 106.6052 | 26.58% | 0 | 6.6736 | 0.18861 | 113.4674 | 25.1122 |  | Work in Progress Need additional Sub contractors |  | 5.12 | 137.0439 | 53.59 | 0.18 | 82.11 |  | 135.88 |  | 121 | 120
Grand Total With Pune |  | 1185.379 | 794.8572 | 94.2513 | 212 | 146.42 |  | 1010.0582 |  | 451.7412 | 558.3169 | 0 | 97.6713 | 797.4108 | 736.6399 |  | 214.7468 |  | 0 | 21.6782 | 0.31863 | 236.7436 | 45.0491 |  |  |  | 25.95 |  | 67.5 | 4.034 | 83.365 |  | 154.899 | 0 | 121 | 183.2204

## Karnataka Q1 Billing Review (hidden)
Q-1 Billing for Pipe project
Sr | Project | code | Amt. In Cr.
1 | Bijapur 24x7 |  | 0.063494 | DONE | S
2 | Pune Project Billing Done Q1 |  | 7.4924 | DONE
3 | Jalgaon Amrut Service bill |  | 3 | DONE | S
4 | Bagalkot Service |  | 1.594 | DONE | S
5 | Bagalkot Material |  | 1.906 | DONE | M
| Total Billing Q-1 |  | 14.0559
1 | Jabalapur | 2500000 | 0.25 | DONE | S
2 | Gokak | 3299999.8 | 0.33 | DONE | S | 0.33
3 | Nipani | 7750000 | 0.775 | DONE | S | 2.08
4 | Bagalkot | 54998977 | 5.4999 | DONE | S | 7.585
| Total | 68548976.8 | 6.8549 |  |  | 9.995
| Total Billing will be in Q-1 |  | 20.9108
5 | Bagalkot | 20801022.3 | 2.0801 | in process

## Pipe SAP 29-06-2024 (hidden)
Jain Irrigation Systems Ltd.,
Details of PIPE Project Billing as on 29.06.2024
Name of Project | SAP code | Work Order Value | O&M Value | Total Billing Upto 29.06.2024 | % | Material up to 29.06.2024 | Services up to 29.06.2024 | Total Billing Q1 | Balance Work Rs. | Gross collection as on Date (Gross RA Bill) | Net collection | % of RA Bill | O/s As on 29.06.24 | % | o/s EMD | o/s SD | o/s Other | Total O/S as on 29.06.2024 | Inventory 29.06.24 | BG O/S as on 29.06.2024 |  |  |  | Billing to be done includuing GST
Balaghat | 20016583 | 38.681 |  | 38.9275 | 100.6% | 16.6939 | 22.2336 | 0 | -0.24654 | 37.2175 | 33.0775 | 96.22% | 2.0657 | 5.34% | 0 | 1.7477 | 6.78e-05 | 3.8134 | 0.16 | 1.9341
JabalPur 24x7 | 20021445 | 19.15 | 2.652 | 16.6812 | 87.11% | 9.4359 | 7.2452 | 0 | -0.18324 | 16.5118 | 15.1437 | 86.22% | 0.19225 | 1.004% | 0 | 0.67398 | 0 | 0.86624 | 0.52 | 1.1412
Total MP |  | 57.831 | 2.652 | 55.6087 |  | 26.1299 | 29.4788 | 0 | -0.42978 | 53.7292 | 48.2212 |  | 2.2579 |  | 0 | 2.4217 | 6.78e-05 | 4.6797 | 0.68 | 3.0752
Bhusawal | 20019598 | 46.5 | 0 | 77.0344 | 165.7% | 28.4379 | 48.5965 | 0 | -30.5344 | 45.0078 | 40.7631 | 96.79% | 32.0422 | 68.91% | 0 | 1.8644 | 0 | 33.9066 | 1.57 | 1
Pune 24x7 | 20020916 | 375.8465 | 42.6389 | 146.325 | 38.93% | 65.6805 | 80.6446 | 7.4924 | 186.8826 | 54.3609 | 48.3798 | 14.46% | 91.9642 | 24.47% | 0 | 3.1474 | 0 | 95.1116 | 0.42 | 25.1122
JMC | 20019869 | 211.0846 | 0 | 211.0759 | 100% | 60.5536 | 150.5222 | 3 | 0.0087582 | 202.6906 | 190.3035 | 96.02% | 8.4664 | 4.011% | 0 | 4.926 | 0.14397 | 13.5363 | 1.883 | 0
Total MH |  | 633.4312 | 42.6389 | 434.4353 |  | 154.672 | 279.7633 | 10.4924 | 156.357 | 302.0593 | 279.4463 |  | 132.4727 |  | 0 | 9.9378 | 0.14397 | 142.5545 | 3.873 | 26.1122
Bijapur 24x7 | 20017531 | 201.79 | 27.7876 | 175.0449 | 86.75% | 62.0774 | 112.9676 | 0.063494 | -1.0425 | 141.363 | 129.345 | 70.05% | 34.8936 | 17.29% | 0 | 2.5968 | 0 | 37.4904 | 6.29 | 13.2215
Bagalkot 24x7 (Original W.O.Value Rs 82.60 Cr) (R WO 39.53 + 9.54 Extra Work = 49.07 + 1.24 Or 2.40 GST = 50.31 or Rs 51.47 Cr) | 20017532 | 56.7351 | 6.4351 | 42.7241 | 75.3% | 18.8179 | 23.9062 | 3.5 | 7.5759 | 35.8501 | 32.4053 | 63.19% | 7.4589 | 13.15% | 0 | 0.69731 | 0 | 8.1562 | 2.46 | 2.59 |  |  | 2.0759 | 7.5759
Nippani | 20014724 | 29.16 | 5.5 | 28.4234 | 97.47% | 11.9387 | 16.4847 | 0 | 0.73655 | 25.5187 | 22.7915 | 87.51% | 2.9774 | 10.21% | 0 | 0.57292 | 0 | 3.5504 | 0.11 | 3.9798 | 29.6634 | Bills Submitted XII QTR : ₹40 Lakhs XIII QTR: ₹40 Lakhs XIV QTR: ₹40 Lakhs XV QTR: ₹40 Lakhs Total Submitted Bills A : ₹160 Lakhs Bills to be Submitted XVI QTR : ₹40 Lakhs XVII QTR : ₹40 Lakhs XVIII QTR : ₹40 Lakhs XIX QTR : ₹40 Lakhs XX QTR : ₹40 Lakhs O&M works Bill: ₹40 Lakhs Total Bills to be Submitted B: ₹240 Lakhs Total A + B= 400 Lakhs |  | 0.77
Gokak | 20013988 | 27.9 | 6.45 | 27.5736 | 98.83% | 12.013 | 15.5606 | 0 | 0.32641 | 26.5386 | 23.9648 | 95.12% | 1.7468 | 6.261% | 0 | 0.090526 | 0.16227 | 1.9996 | 0.084503 | 3.0253 |  |  |  | Done-0.33
Haliyal | 20013802 | 19.13 | 5.6897 | 19.2162 | 100.5% | 6.2805 | 12.9357 | 0.004291 | -0.086176 | 18.8626 | 17.6636 | 98.6% | 0 | 0% | 0 | 0 | 0.010431 | 0.010431 | 0.0057755 | 0
Total KA |  | 334.7151 | 51.8624 | 292.9823 |  | 111.1276 | 181.8547 | 3.5678 | 7.5102 | 248.1331 | 226.1703 |  | 47.0768 |  | 0 | 3.9576 | 0.1727 | 51.2071 | 8.9503 | 22.8166
PHE,Yamunanagar | 20024063 | 20.07 | 0.43251 | 19.72 | 98.26% | 18.0674 | 1.6526 | 0 | 0.34997 | 19.785 | 19.1729 | 98.58% | -0.031141 | -0.1552% | 0 | 0.0072085 | 0.0021625 | -0.02177 | 0.033 | 0
PHE Rewari | 20019189 | 40.47 | 0.99 | 40.1989 | 99.33% | 36.9702 | 3.2287 | 0 | 0.27105 | 39.9827 | 38.5266 | 98.8% | 0.27949 | 0.6906% | 0 | 0 | 0 | 0.27949 | 0 | 0
PHE Bawal | 20019190 | 7.2408 | 0.18102 | 7.2092 | 99.56% | 6.078 | 1.1312 | 0 | 0.031664 | 7.2092 | 6.712 | 99.56% | 0.073162 | 1.01% | 0 | 0.33358 | 0.0006517 | 0.4074 | 0 | 0
PHE,Jind | 20024433 | 15.24 | 0.39616 | 15.3285 | 100.6% | 12.7981 | 2.5304 | 0 | -0.088483 | 14.8412 | 13.688 | 97.38% | 0.52214 | 3.426% | 0 | 0.58202 | 0 | 1.1042 | 0 | 0
CHARKHI DADRI | 20025083 | 27.82 | 0.78789 | 30.9755 | 111.3% | 27.911 | 3.0645 | 0 | -3.9434 | 27.0367 | 23.8572 | 97.18% | 3.4575 | 12.43% | 0 | 2.9437 | 0 | 6.4013 | 0.013 | 0
PHE,TOHANA | 20026203 | 31.07 | 0 | 32.9358 | 106% | 31.1741 | 1.7616 | 0 | -1.8658 | 31.0694 | 26.9758 | 100% | 1.8664 | 6.007% | 0 | 3.2408 | 0 | 5.1072 | 0.15 | 0
Total HR |  | 141.9108 | 2.7876 | 146.3679 |  | 132.9989 | 13.369 | 0 | -5.2449 | 139.9242 | 128.9324 |  | 6.1676 |  | 0 | 7.1073 | 0.0028142 | 13.2777 | 0.196 | 0
Grand Total |  | 1167.8881 | 99.9409 | 929.3942 |  | 424.9283 | 504.4658 | 14.0601 | 196.1828 | 743.8458 | 682.7702 |  | 187.9751 |  | 0 | 23.4243 | 0.31955 | 211.719 | 13.6993 | 52.004

## Karnataka WS project 20th April (hidden)
100
1.03
Project | WO Value | Capex | O&M | Dept Bill | SAP | O/s | SD | Other O/s | Total O/s | Balance work | Receivable Payment | Issues | Manpower | Remark
Gokak | 28.5 | 21.45 | 7.05 | 26.54 | 27.57 | 1.75 | 0.54 | 0.17 | 2.46 | NIL. O&M completed. Completion Certificate recd. Balance material stock shifted to Bijapur | 2.0 Cr | Flood Damage & O&M works payment from CMC Fund. Dept deducted 13 lakh as VAT in 18th RA in GST Regime. Needs to Get back | Jisl staff Transfer to Bijapur & Bagalkot. Lokesh Sanadi retained for balance payment follow up | Accnt to be Reco SAP vs Dept
Nipani | 29.02 | 23.52 | 5.5 | 24.96 | 28.42 | 3.51 | 0.57 |  | 4.08 | 1 year O&M | 4.3 | Dept not paid our O&M payment sinc last one year. Expecting 11th Quatrter & consumable payment 48 lakh. Issue of non transfer of PAyment to ESCROW accnt from KUIDFC to CMC | JISL Pay Roll - 3 nos Contract Staff-39 nos
Bijapur | 201.79 | 174 | 27.79 | 141.36 | 174.98 | 2.65 | 26.5 | 0.15 | 29.3 | 15 nos Chlorinator, 3 nos Zone Commissioning Meter fixing 3000 nos Sluice valve 180 nos EMF meter 12 nos PRV 13 nos Valve box fixing 1500 Nos | 17.82 | Bulk water Suppply fm KUIDFC,unauthorized HSC,mter issue Variation ,,GST yet not approved Dishonest JISL Payroll staff | JISL Pay Roll - 11 nos Contract Staff-44 nos
Bagalkot | 53.94 | 47.5 | 6.44 | 35.85 | 39.22 | 3.96 | 0.7 | 0.1 | 4.76 | Pontoon shifting to deep water and cable and risng main flaoting in lake. Balance HSC &Meter Fixing -600 nos | 5.25 |  | JISL Pay Roll - 4 nos Contract Staff-13 nos
3 town | [10 empty] | 1.25 cr

## SAP acnt 30th April 24 (hidden)
Jain Irrigation Systems Ltd.,
Details of PIPE Project Billing as on 30.04.2024
Name of Project | SAP code | Work Order Value | O&M Value | Total Billing Upto 30.04.2024 | % | Material up to 30.04.2024 | Services up to 30.04.2024 | Total Billing Q1 | Balance Work Rs. | Gross collection as on Date (Gross RA Bill) | Net collection | % of RA Bill | O/s As on 30.04.2024 | % | o/s EMD | o/s SD | o/s Other | Total O/S as on 30.04.2024 | Inventory 08.09.2023 |  | BG O/S as on 31.03.2024
Balaghat | 20016583 | 38.681 |  | 38.9275 | 100.6% | 16.6939 | 22.2336 | 0 | -0.24654 | 37.2175 | 33.0775 | 96.22% | 2.0657 | 5.34% | 0 | 1.7477 | 6.78e-05 | 3.8134 | 0.11141 |  | 0
JabalPur 24x7 | 20021445 | 19.15 | 2.652 | 16.6812 | 87.11% | 9.4359 | 7.2452 | 0 | -0.18324 | 15.7333 | 14.4312 | 82.16% | 0.90476 | 4.725% | 0 | 0.67398 | 0.026363 | 1.6051 | 0.099803 |  | 1.1412
Total MP |  | 57.831 | 2.652 | 55.6087 |  | 26.1299 | 29.4788 | 0 | -0.42978 | 52.9507 | 47.5087 |  | 2.9705 |  | 0 | 2.4217 | 0.026431 | 5.4185 | 0.21122 |  | 1.1412
Bhusawal | 20019598 | 46.5 | 0 | 77.0344 | 165.7% | 28.4379 | 48.5965 | 0 | -30.5344 | 45.0078 | 40.7631 | 96.79% | 32.0422 | 68.91% | 0 | 1.8644 | 0.045728 | 33.9523 | 0.27938 |  | 1
Pune 24x7 | 20020916 | 375.8465 | 42.6389 | 140.4722 | 37.37% | 59.8277 | 80.6446 | 1.6395 | 192.7354 | 54.3609 | 48.3798 | 14.46% | 86.1113 | 22.91% | 0 | 3.1474 | 0.23321 | 89.492 | 0.17313 |  | 25.1122
JMC | 20019869 | 200 | 0 | 6 | 3% | 60.5536 | 147.5222 | 0 | 194 | 202.6906 | 190.3035 | 101.3% | 5.4664 | 2.733% | 0 | 4.926 | 0.68018 | 11.0725 | 2.2517 |  | 0
Total MH |  | 622.3465 | 42.6389 | 223.5066 |  | 148.8192 | 276.7633 | 1.6395 | 356.201 | 302.0593 | 279.4463 |  | 123.6199 |  | 0 | 9.9378 | 0.95912 | 134.5168 | 2.7042 |  | 26.1122
Bijapur 24x7 | 20017531 | 201.79 | 27.7876 | 175.0449 | 86.75% | 62.0774 | 112.9676 | 0.063494 | -1.0425 | 141.363 | 129.345 | 70.05% | 34.8936 | 17.29% | 0 | 2.5968 | 0.1508 | 37.6412 | 5.4737 |  | 13.2215
Bagalkot 24x7 | 20017532 | 47.44 | 6.4351 | 39.2241 | 82.68% | 16.9093 | 22.3149 | 0 | 1.7807 | 35.8501 | 32.4053 | 75.57% | 3.9589 | 8.345% | 0 | 0.69731 | 0.10015 | 4.7564 | 2.6465 |  | 4.1302
Nippani | 20014724 | 30.5 | 5.5 | 28.4234 | 93.19% | 11.9387 | 16.4847 | 0 | 2.0766 | 24.9623 | 22.2587 | 81.84% | 3.5103 | 11.51% | 0 | 0.57292 | 0 | 4.0832 | 0.071809 |  | 4.8938
Gokak | 20013988 | 27.9 | 6.45 | 27.5736 | 98.83% | 12.013 | 15.5606 | 0 | 0.32641 | 26.5386 | 23.5198 | 95.12% | 1.7468 | 6.261% | 0 | 0.53554 | 0.17374 | 2.4561 | 0.084503 |  | 3.0253
Haliyal | 20013802 | 19.13 | 5.6897 | 19.2119 | 100.4% | 6.2805 | 12.9314 | 0 | -0.081885 | 18.8626 | 17.6636 | 98.6% | -0.004291 | -0.02243% | 0 | 0 | 0.010431 | 0.00614 | 0.0057755 |  | 0
Total KA |  | 326.76 | 51.8624 | 289.478 |  | 109.2189 | 180.2591 | 0.063494 | 3.0593 | 247.5767 | 225.1924 |  | 44.1054 |  | 0 | 4.4026 | 0.43513 | 48.9431 | 8.2823 |  | 25.2708
PHE,Yamunanagar | 20024063 | 20.07 | 0.43251 | 19.72 | 98.26% | 18.0674 | 1.6526 | 0 | 0.34997 | 19.749 | 18.8913 | 98.4% | 0 | 0% | 0 | 0.26 | 0.0010092 | 0.26101 | 0.036273 |  | 0
PHE Rewari | 20019189 | 40.47 | 0.99 | 40.1989 | 99.33% | 36.9702 | 3.2287 | 0 | 0.27105 | 39.9827 | 38.4774 | 98.8% | 0.32942 | 0.814% | 0 | 0 | 0 | 0.32942 | 0 |  | 0
PHE Bawal | 20019190 | 7.2408 | 0.18102 | 7.2092 | 99.56% | 6.078 | 1.1312 | 0 | 0.031664 | 7.2092 | 6.5074 | 99.56% | 0.073162 | 1.01% | 0 | 0.53816 | 0.0006517 | 0.61197 | 0 |  | 0
PHE,Jind | 20024433 | 15.24 | 0.39616 | 15.3285 | 100.6% | 12.7981 | 2.5304 | 0 | -0.088483 | 14.8412 | 13.3715 | 97.38% | 0.52214 | 3.426% | 0 | 0.89845 | 0 | 1.4206 | 0 |  | 0
CHARKHI DADRI | 20025083 | 27.82 | 0.78789 | 30.9755 | 111.3% | 27.911 | 3.0645 | 0 | -3.9434 | 27.0367 | 22.3572 | 97.18% | 4.9575 | 17.82% | 0 | 2.9437 | 0.10826 | 8.0095 | 0.091915 |  | 0
PHE,TOHANA | 20026203 | 31.07 | 0 | 32.9358 | 106% | 31.1741 | 1.7616 | 0 | -1.8658 | 31.0694 | 26.9758 | 100% | 2.0181 | 6.495% | 0 | 3.2408 | 0.06193 | 5.3208 | 0.38505 |  | 0
Total HR |  | 141.9108 | 2.7876 | 146.3679 |  | 132.9989 | 13.369 | 0 | -5.2449 | 139.8882 | 126.5806 |  | 7.9003 |  | 0 | 7.8811 | 0.17185 | 15.9533 | 0.51324 |  | 0
Grand Total |  | 1148.8484 | 99.9409 | 714.9612 |  | 417.1669 | 499.8702 | 1.703 | 353.5856 | 742.4749 | 678.728 |  | 178.596 |  | 0 | 24.6431 | 1.5925 | 204.8317 | 11.7109 | 0 | 52.5242

## A3 summary (hidden)
PIPE PROJECTS COMPLETION | [11 empty] | 5.24
Sr No | Project | PO Amt Cr | CAPEX | O&M | RA BILLS Submitted | SAP | Noraml O/.s | O/S incl SD/EMD 12/02/24 | BALANCE WORKS | EOT Status | TARGET COMPLETION DATE | O & M Status | Comment from Purchase | Pending jobs/ Actions | Possible billing in March 24
PMD/ SAD Wherever penalties are levied, we should represent and get waiver. Wherever feasible, should submit BG and get back our SD/ EMD amount in March. Penalty levied entries are pending. If any Goods are returned and Shifted, accounting to be done. Thanks. Ajit
1 | Rewari | 40.46 | 39.48 | 0.98 | 39.98 | 40.2 | 0.33 | 0.33 | 12 months of O&M | NA | Capex Completion Certificate Received | 4th Yr O&M in Process. 1.0 yrs remaining. completion by 26/2/2025 |  | Payment is being received monthly. Will collect 10 Lakh by March 2024. All payment will be received by June 2024
2 | Bawal | 7.21 | 7.03 | 0.18 | 7.21 | 7.21 |  | 0.61 | 5 months of O&M | NA | Capex Completion Certificate Received | 5th Yr O&M in Process. Completion by 01/7/2024 |  | Rs 13.36 Lakh receivable from ICICI Bank, (Matter to be taken up with bank. Send legal notice) 12 Lakh by March 2024. Balance receivable Rs 35.64 Lakh by August 2024.
3 | Jind | 15.24 | 14.84 | 0.4 | 14.84 | 15.33 | 0.56 | 1.59 | 3.5 years of O&M | NA | Capex Completion Certificate Received | 2nd Yr O&M in Process. Completion by 30/8/2027 |  | Normal O/s 0.59 cr. We will recieve 40 on account of O&M. GR CN - 19 Lacs Security deposits Rs 50 lacs will be received by June 2024. & Balance Rs 50 Lakh after completion of O & M. Rs 3 lacs TDS will be collected in MArch
4 | Yamuna nagar | 20.07 | 19.64 | 0.43 | 19.75 | 19.63 | -0.03 | 0.41 | 3.5 years of O&M | NA | Capex Completion Certificate Received | 2nd Yr O&M in Process. Completion By 30/8/2027 |  | Rs 70 Lakh will be received by June and balance 70 Lakh after completion of O & M.
5 | Charkhi Dadri | 27.81 | 27.03 | 0.78 | 27.04 | 30.98 | 4.96 | 8.01 | 4.00 years of O&M | NA | Capex Completion Certificate to be taken | 1st Yr O&M in Process. Completion by 30/3/2028 |  | Capex Completion Certificate Received. Receivable 1.5Cr Capex Final Bill in March 24 60 lakh credit note for Material return. Fire Claim 3 Cr is expected. Rs 11 lacs TDS will be collected SD rs 2.94 is receivable. Rs 1.47 Cr will be received after 6 months of final payment by Sept 24. Balance 1.47 Cr will be received after O&M is completed. | Explore collection of SD against submission of BG
6 | Tohana | 31.06 | 31.06 | - | 31.07 | 32.93 | 2.08 | 5.33 | Completed | NA | Capex Completion Certificate to be taken | NO O&M |  | Completion Certificate will be collected in March. Fire claim 2.10Cr is expected Rs 5 lacs TDS will be collected in March. SD - 3.20 Cr will be collected in Sept 24. | Explore collection of SD against submission of BG
| Total Haryana | 141.85 | 139.08 | 2.77 | 139.89 | 146.28 |  | 16.28 | [5 empty] | Wherever penalties are levied, we should represent and get waiver. Wherever feasible, should submit BG and get back our SD/ EMD amount in March. As all the sites are completed and handed over. Most of the sites O&M is also over. Take back all the inventory/ material including scrap. Thanks. Ajit
7 | Balaghat | 38.68 | 38.68 |  | 36.64 | 38.93 |  | 3.85 | Completed, Handover Balance | NA | 31st March 24 | We are maintaining since last 3 yrs after 3 months trial Run |  | New 500 HSC/meter to be installed . additional material-water meter 425 nos90 mm ef tapping tee 500 nos TArget to HAndover by 30th JUne
8 | Jabalpur | 19.15 | 16.5 | 2.65 | 14.62 | 15.38 | 0.72 | 1.35 | SCADA work in final stage, AMR Meter Water meter Box installation -2300 nos. HSC /AMR mter installation in progress as per JSCL LIst/Receipts. Billing Software work in progress. 500 mtr pipe line work Balance for dept clearance issues | Applied Upto March 2024 | 2024-04-24 | 5 yrs -yet to start |  | Capex Short close -1 DMA cancelled. Targeted Completion 30st june 24. | Water meter Box 10 lakh 25 lakh Service
| Total | 57.83 | 55.18 | 2.65 | 51.26 | 54.31 |  | 5.2 | [5 empty] | Wherever penalties are levied, we should represent and get waiver. Wherever feasible, should submit BG and get back our SD/ EMD amount in March. As all the sites are completed and handed over. Most of the sites O&M is also over. Take back all the inventory/ material including scrap. Thanks. Ajit
9 | Bhusawal | 47 | 47 | - | 45 | 77.03 | 29.06 | 30.85 | A..2 nos ESR Top slab work in Progress, Vertical Ppes and Finsing Work Balance. B.2 NOs ESR BOttom Slab work in Progress, Blance work Container wall, top slab, Vertical Pipes & Finishing. C. 6 Nos NOS ESR - Vertical pipe installation in Progress, Finishing Balance. D. Hydrotesting of ESR- but non avilability of Water for testing from BMC |  | 31st March- Amrut 1.0 Closing But 2 nos ESR works may Reuire time to June End. | NO O&M |  | A..2 nos ESR Top slab work in Progress, Vertical Ppes and Finsing Work Balance. B.2 NOs ESR BOttom Slab work in Progress, Blance work Container wall, top slab, Vertical Pipes & Finishing. C. 6 Nos NOS ESR - Vertical pipe installation in Progress, Finishing Balance. D. Hydrotesting of ESR- but non avilability of Water for testing from BMC
10 | Jalgaon Amrut | 204 | 204 | - | 202.69 | 199.08 | NIL | 5.61 | Railway Crossing and Additional HSC work 1000 nos.. Finishing work of Nityanand & MIDC ESR. Instlllation &Testing Additional pipeline 1 km Road resoration1.20km WTP renovation -40% Balance |  | 15th March 24 | NO O&M |  | Railway Crossing in Progress. Additinal HSC in Progress.
11 | Pune | 375.85 | 333.21 | 42.64 | 50.6 | 103.15 | 52.54 | 55.55 |  |  | Capex 31/12/24 | 10 yrs |  | DI pipes, 3rd Lot AMR meters, DI fittings, EMF meters, Valves req for 7 nos Zone commissining | Billed 11.5 cr in Q4
| Total | 626.85 | 584.21 | 42.64 | 298.29 | 379.26 |  | 92.01 | [5 empty] | Wherever penalties are levied, we should represent and get waiver. Wherever feasible, should submit BG and get back our SD/ EMD amount in March. As all the sites are completed and handed over. Most of the sites O&M is also over. Take back all the inventory/ material including scrap. Thanks. Ajit
12 | Gokak MC | 28.5 | 21.45 | 7.05 | 26.5 | 26.98 | 3.13 | 3.8 | 1 month of O&M | NA | 31/3/24 | 5th Yr O&M in Process. 31/3/2024 | NA | Project is handed over .Completion Taken All Final Bills and O & M bills upto 20th Q are submitted. SD release of Rs 0.57 Cr by march End Final bills RS 1.776 Cr payment by 31 March 2024. O&M works & Flood Damage payment of 2.0 Cr shall be paid fm CMC fund Labour Payments to be cleared from September 2023 to February 2024 | Billing 1.02 Cr
13 | Nipani MC | 30.5 | 25 | 5.5 | 24.96 | 27.54 | 2.62 | 3.2 | 1.0 Years of O&M | NA | 31/3/25 | 4th Yr O&M in Process. 31/3/2025 | NA | Alum, Chlorine require on Monthly Basic. PO Given. Vendor and Labour Payments are balance. Final Bill of 40 lakh in Process O&M Bill Q 11 to 14 of RS 1.4 Cr- at Bangalore Bill of 0.3 Cr of O&M works in process Further Q 15 to 20 Manpower 2.22 Cr SD Rs 57 lacs Vendor and Labour payment balance | Receivable Till completion of O&M Rs 4.30 Cr . 4.30 cr less O/s 2.62 = Bal Billing 1.68 Cr March Proposed billing Q 15 &16 O&M = 65 lakh
14 | Bijapur | 201.79 | 174 | 27.79 | 141.36 | 174.98 | 34.83 | 37.58 | Trial Run & Commissioning- 1 Nos Zones, Due to bulk shortage WIP HSC - 850 nos EMF- 15 nos PRV-23 nos Valve Chamber 49 Nos, Surface Box Fixing 797 nos, Regularization & Survey of HSC- 8000 nos ( WIP) Supply &fixing of Chlorinator -15 nos Replacement of Old Valves at WTP 62 nos WIP | Applied Upto March 2024 | Capex by 15/3/24 | Enter Into O&M from 1st Jan 24 | 1. Need funds of Rs. 26 Lacs for chlorinators. Not accepting L/C as unable to take LC. | 1.No Suffiecent Bulk water Supply from CMC for Zone Commssioning. 2. Require Chlorinator 15 nos fm vendor Group Industries 3. Require Water meter 3000 nos 4. Bill Of Rs 7.63 Cr is in process of payment. RS 14.32 Cr is with held for Variation praposal approval, measurments recorded. Final Bill of Rs 2.5 Cr to be prepared Feb 2024 end. 5. GST of RS 4.41 Cr is in Process. EMD/ SD - Rs 10 lacs 6. Vaendor Payments, Since last 4 Months Labour Payments is balance. 2.5 Cr Penalty Waiver. Request for extra work and do it. Make sure that there will be NO short closing. | Likely Short closing of 12.83 Cr.
15 | Bagalkot | 46.44 | 40 | 6.44 | 35.85 | 37.83 | 2.57 | 3.37 | Pontoon Pump 300 HP- Supply &Installation 2 nos Pontoon Electric Work 1 nos, Scada Balance works Zone commissioning 5 nos- Under Progress | Applied Upto March 2024 | Capex by 15/3/24 |  |  | 1. Floaters 200 mm /160 mm 2. Tug Boat/ Flexible pipe 3. Final Bill approximately 4 Cr possible after Pontoon work complation. 4. GST bill Rs 1.24 Cr in Process. 5. SD Rs 80 lacs to be collected 6. Penalty Waiver | Billing 2.67 cr
16 | Haliyal | 19.13 | 13.44 | 5.69 | 18.86 | 19.13 |  | 0.15 | NIL |  | Completed | Completed | NA | Project handed over. O & M Complete. Certificate collected. All Payment received | There is difference in figures. Check calculations & update. Raise Bill - 7.5 lacs approximately
17 | Dharwad | [6 empty] | 1.3244 | [5 empty] | Project and O & M completed. Certificate and due Payment Rs 1.25 Cr will be collected.
| Water projects Total | 326.36 | 273.89 | 52.47 | 247.53 | 286.46 |  | 49.4244 | [5 empty] | Wherever penalties are levied, we should represent and get waiver. Wherever feasible, should submit BG and get back our SD/ EMD amount in March. As all the sites are completed and handed over. Most of the sites O&M is also over. Take back all the inventory/ material including scrap. Thanks. Ajit

## bGK balance 30-4-24 (hidden)
Bagalkot Project Details
Sl No | Particulars | Unit | Amount | Remarks
1 | Capex Value | Rs | 761678885.79
2 | O&M value | Rs | 64351487.49
3 | Variation Proposal Amount | Rs | 490661297.1487
4 | Gross Dept Bill till Date Amt excluding Mobilization advance | Rs | 361447760
5 | Dept bill in Progress Amt | Rs | 12451463.96 | Awaiting EOT |  |  | Bill in Process | 1.25
6 | Balance Receivable Amount till project completion |  |  |  | Balance Receivable Amount till project completion |  | Commissioning | 0.5
| as per BOQ | Rs | 400231125.8 |  | as per BOQ |  | EIRL | 5.3
| as per actual | Rs | 129213537.1 |  | as per actual | 12.9214 | Workslip | 2.2
7 | commissioning | Rs | 4871707.04 |  | commissioning | 0.48717 | GST difference | 2.45
8 | EIRL | Rs | 52510583.1465 |  | EIRL | 5.2511 | Total | 11.7
9 | Workslip | Rs | 21723068.8028 |  | Workslip | 2.1723
10 | GST diff | Rs | 24501915.81 |  | GST diff | 2.4502
11 | Balance Work activity wise with targeted completion date |  |  |  |  | 23.2821
| Meter Fixing | Days | 15
| Flushing and inter connection | Days | 20
| Pontoon Erection (after receiving Floaters) | Days | 10 | Awaiting Floaters
| SCADA |  |  | Awaiting SCADA Team at site for final trial run and detailed report will be sent shortly
12 | Priority Material required
| GI Collar 15mm | Nos | 1500 | As per IS 779-1994
| 90mm HDPE PN-8 Elbow - Fabricated | Nos | 10
| Water Meter 15mm | Nos | 560 | 15mm nominal bore- NP
| Water Meter protection Box | Nos | 150 | Brass Ball valve with plastic float conforming to relavent ISS
| Bib cock 15mm | Nos | 580
| Ball Valve 15mm | Nos | 380
| GI Tee 15mm | Nos | 500
| GI Elbow | Nos | 500
13 | Other Issues
Payments for Labours, rented Vehicles from the month of February by Shri Mukambika Builders
| vendor payments needs to be cleared at the earliest |  |  | Afroz Navaldar

## JMC bill 3cr (hidden)
HDPE DIV
Client: | Commissioner, Jalgaon MC |  |  |  | HDPE Div
ZJCP DC 13 GST 18% |  |  | HSN 9954
Sap code | 20019869 |  |  |  |  | Bill 1
Storage Location |  | MH05
S.No | TEXT IN BILL | SAP code | HSN | Order Type | Amt | GST 18% | Total amt
1 | WTP renovation | INSTPROJECT | 9954 | ZJCP | 4878940 | 878209.2 | 5757149.2
Bill 2
S.No | Item | SAP code | HSN | Order Type | Amt | GST 18% | Total amt
2 | Interconnections | INSTPROJECT | 9954 | ZJCP | 5463200 | 983376 | 6446576
Bill 3
S.No | Item | SAP code | HSN | Order Type | Amt | GST 18% | Total amt
3 | Concrete Roads | INSTPROJECT | 9954 | ZJCP | 4510025 | 811804.5 | 5321829.5
Bill 4
S.No | Item | SAP code | HSN | Order Type | Amt | GST 18% | Total amt
4 | Road crossings | INSTPROJECT | 9954 | ZJCP | 5648230 | 1016681.4 | 6664911.4
Bill 5
S.No | Item | SAP code | HSN | Order Type | Amt | GST 18% | Total amt
5 | ESR finishing work | INSTPROJECT | 9954 | ZJCP | 4923670 | 886260.6 | 5809930.6
30000396.7
25423728.81
5084745.763

## 22-Mar-24 (hidden)
PIPE PROJECT BALANCE BILLING
Till date in Q 4= |  | 11.30 Cr
Project | Type | Balance | Remark
Pune | Water meter | 1.94 | IN transit | 3.24 | 1..94
| Service | 22 | service | 20
Sub total pune |  | 23.94
Nipani | 2 Quarter O&M-15th &16th | 0.65 | service
Gokak |  | 1 | service | 0
BGK | Material | 2.2627 | material | 1.17
Jablpur | Meter Box | 0.1 | material
Jablpur | Service | 0.25 | service
Mastek | M/c Rental | 0.1 | service
Haliyal | Service | 0.07 | service
Jalgaon | Service | 5.0847 | Service
Total |  | 33.4575
MARCH 24 SALE
Pls. find below herewith Project Sales for Mar-24 |  | 19:00
|  |  | Material | Service
Payer | Payer Name | Amount
20020916 | MUNICIPAL COMMISSIONER PMC 24X7 PRO | 345478391 | 139269223.7 | 206209167.33 | 226195608 | 6209680.17 | 199999487.16
20014724 | COMMISSIONER, CMC, NIPANI | 7512659 | 944863 | 6567796 |  | 1114938.34 | 7749999.28
20017532 | KUWS& DB -BAGALKOT 24X7 | 11786594 | 11786594 |  |  |  | 13908180.92
20013802 | THE CHIEF OFFICER,TOWN PANCHAYAT,HA | 658109 |  | 658109 |  | 26.6798 |  | 776568.62
20019869 | THE COMMISSIONER JCMC -AMRUT WSS | 50800000 |  | 50800000 |  | 16.4374
20021445 | CEO, JABALPUR SMART CITY LIMITED | 3534747 | 1035000 | 2499747 | 2949701.46
20027900 | ITC LIMITED-PSPD-BCM | 147500 | 147500 |  |  | 5.9944
| Mastek - 1600 mm Machine rental | 1000000 |  | 1000000
| Ceinsys Tech -Thane | 875000 |  | 875000
| TOTAL BILLING DONE | 421793000 | 153183180.7 | 268609819.3
Balance Billing
| Pune Service |  |  | 19986440.68 |  | 365464831.7 | 431248501.4
| Balaji traders,Abhor M/C rental |  |  | 60000
| Gokak |  |  | 5000000 |  | 5900000
| Jabalpur servcie |  |  | 5000000 |  | 50
| TOTAL BILLING BALANCE |  |  | 30046440.68
| GROSS MARCH 24 | 451839440.7 | 153183180.7 | 298656260

## Tohana (hidden)
Name of Project |  | Tohana
Targeted Completion Date |  | Completed in June 23, Final bill in process
PO Value |  | 32.89 Cr
Gross Bill Till Date |  | 30.27 Cr | Closing 31.06 Cr |  | Final Bill in Process 0.79 Cr
SAP Billing |  | 32.93 cr
Fire claim |  | 2.47 Cr | Awaited
Project Manager |  | S.K. Pal
Balance Days for Completion
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date | Receivable as Per Site Manager | O/S Normal | O/S SD/EMD | BG
[12 empty] | 2025-09-12 02:31 | incl SD/EMD
| Work Complted in June 23, Final Bill recording in process |  |  |  |  | Completion Certificate to be taken afater Final Bill Recording | [6 empty] | #REF! | #REF! | #REF! | NIL
Baalnce Material
Sr No | Material | Qty | Unit | STO/PR/PO |  | Vendor | Status

## Ch Dadri (hidden)
Ch Dadri |  | Ch Dadri
Targeted Completion Date |  | Completed
PO Value |  | 28.47 Cr | Capex | 27.69 Cr | O&M | 0.78 Cr
Gross Bill Till Date |  | 21.62 Cr |  | Closing | 27. 03 Cr
SAP Billing |  | 30.97 Cr
Fire Claim received |  | 0.48 Cr
Fire Claim |  | 3.11 Cr | Awaited
Project Manager |  | S.K. Pal
Balance Days for Completion
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date
2025-09-12 02:31
1 | Completed in March 2023 , Final Bill Balance , Ist Year O&M in process
Material Requirement
Sr No | Material | Qty | Unit | STO/PR/PO |  | Vendor | Status
1 | NIL

## Bhuswal (hidden)
Name of Project |  | Bhusawal
Targeted Completion Date |  | 2024-06-30
PO Value |  | 84.58 Cr | Short close 47 Cr
Gross Bill Till Date |  | 45 | Balance Billing 2.0 Cr
SAP Billing
Project Manager |  | Nitin. A. Chaudhari
Balance Days for Completion |  | #NAME?
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date | Receivable as Per Site Manager | O/S Normal | O/S SD/EMD | BG
2025-09-12 02:31
1 | ESR Zone 1- 20 lakh Lit Cap .- Balance Work - , top slab work in progress, DI PIpe Assembly ,finishing, Hydro testing | 25% |  | #NAME? | 60 | Top slab centring in process | Contractor- Beton Kraft |  |  | Water for testing | Additional manpower to be enggaed by existing contr | 1
2 | ESR Zone 2 Cap 15.40 Lakh lit -- Balance Work - , top slab casting balance, DI PIpe Assembly finishing, Hydro testing | 30% |  | #NAME? | 120 | Top slab casting to be done | Contractor -Ideacrete |  |  | Water for testing | Additional manpower to be enggaed by existing contr | 1
3 | zone 3-Cp 11.20 lakh lit- Balance Work -finishing , pipe assebly, Hydro testing | 22% |  | #NAME? | 90 | DI pipe Supply started | Contractor- Beton Kraft |  |  | Water for testing | Additional manpower to be enggaed by existing contr
4 | zone 4-Cap 8.75 Lakh Lit- Balance Work -finishing , pipe assebly, Hydro testing | 22% |  | #NAME? | 120 | DI pipe Supply started | Contractor- Beton Kraft |  |  | Water for testing | Additional manpower to be enggaed by existing contr
5 | ESR zone 5- Cap 5.15 lakh Lit -Balance Work -finishing , pipe assebly, Hydro testing | 22% |  | #NAME? | 120 | DI pipe Supply started | Contractor -Ideacrete |  |  | Water for testing | Additional manpower to be enggaed by existing contr | 1
6 | ESR zone 6- CAp 11.85 Lakh Lit-Balance Work -finishing , pipe assebly, Hydro testing | 22% |  | #NAME? | 60 | DI pipe Supply started | Contractor -Ideacrete |  |  | Water for testing | Additional manpower to be engaed by existing contr | 1
7 | ESR zone 7-Cap 11.05 Lakh Lit- Balance Work- Bottom slab in process, container wall, top slab, finishing, Pipe Assembly, Hydro testing | 64% |  | #NAME? | 120 | increasing contr team | Contractor- Beton Kraft |  |  | Water for testing | Additional manpower to be engaed by existing contr | 1
8 | ESR Zone 8- cancelled- due to Encrachment on ESR place |  |  | #NAME? | N.A. | [6 empty] | 7
9 | ESR zone 9-Cap 11.10 lakh lit- Balance Work- , finishing, Pipe Assembly, Hydro testing | 22% |  | #NAME? | 75 | DI pipe Supply started | Contractor- Beton Kraft |  |  | Water for testing | Additional manpower to be engaed by existing contr
10 | ESR zone 10-Cap 15 lakh lit - Balance Work- Bottom slab in process, contianer wall, top slab, finishing, Testing | 64% |  | #NAME? | 130 | bottom slab work in progress | Contractor -Ideacrete |  |  | Water for testing | Additional manpower to be engaed by existing contr
11 | ESR zone 11-Cap 5.95 lakh lit- Balance Work -finishing , pipe assebly, Hydro testing | 22% |  | #NAME? | 45 | DI pipe Supply started | Contractor -Ideacrete |  |  | Water for testing | Additional manpower to be engaed by existing contr
Material Requirement
Sr No | Material | Qty | Unit | STO/PR/PO |  | Vendor | Status
1 | DI Double flange PIpes for INlt & Outlet pipes of ESR |  |  |  |  | Upadhay valve- PO amt 1.35 Cr +GST | duck foot bend and some pipes balance
As per Purchase vendor will send in 2 days

## Jalgaon (hidden)
Name of Project |  | Jalgaon
Targeted Completion Date |  | 2024-03-15
PO Value |  | 184 Cr | Revised | 203.73 Cr
Gross Bill Till Date |  | 194.59 Cr
SAP Billing |  | 200 Cr
Project Manager |  | Pankaj Barhate
Balance Days for Completion |  | #NAME?
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date | Receivable as Per Site Manager | O/S Normal | O/S SD/EMD | BG
2025-09-12 02:31
154
1 | HDPE Pipeline-Additional Scope | 1 | KM | #NAME? |  | 15 | [5 empty] | 1
2 | House Service Connection ( Additional) | 1000 | Nos | #NAME? |  | 28 |  |  |  |  | Tapping Tee
3 | Hydrotest -Additional scope pipeline | 1 | KM | #NAME? |  | 15
5 | ESR Of Nityanand CAP 1.5 ML | 1% | % | #NAME? |  | 15 | [5 empty] | 1
6 | ESR Of MIDC CAP 2.5 ML | 3% | % | #NAME? |  | 28 | [5 empty] | 7
7 | Renovation to existing filtration Plant | 40% | % | #NAME? |  | 28 |  |  |  | Filter media decision pending
8 | Railway Crossing | 100% |  | #NAME? |  | 28 |  |  |  |  | MS pipe Required
9 | Road restoration-MPM for road | 0.5 | KM | #NAME? | [6 empty] | Depend On Pipeline work
10 | Road restoration -Carpet & Seal coat for road | 0.5 | KM | #NAME?
11 | Road restoration-Concrete Road | 0.2 | KM | #NAME?
Material Requirement
Sr No | Material | Qty | Unit | STO/PR/PO |  | Vendor | Status
1 | HSC Tapping Tee 110 mm x 20 mm | 1000 | nos |  |  | GF | Material ready
| M.S. Pipe 1200 mm for railway crossing | 132 | mtr |  |  | Ashwamedh Engg | QAP approval given
| M.S. Pipe 813 mm for Railway crossing | 132 | mtr |  |  | Ashwamedh Engg | QAP approval given
| Instllation Agency for HDD to be finalized | [5 empty] | 2 nos Qtn & BOQ given to Purchase for Finalization

## Bijapur Receivable (hidden)
Particulars | Amount | Remarks | 16/12/23
Received Upto date | 1413600000 |  |  | 7.54 |  | 1413600000
Withhold against BOQ | 0 | Submitted in the 28th RA Bill, It will be released in the 28th RA Bill LOC
Withhold against Varaition | 127987687 | Awaiting for the approval of the varaition by KUWSDB
Withhold against EIRL | 16397689.57 | Awaiting for the approval of the varaition by KUWSDB
Withhold against GST | 45200000 | We have submitted te GST, but the format has been revised by the newly appointed CA of KUWSDB, Calculation as per new format WIP
Withhold against Commisioning of works | 26542354 | To be released after the submission of the final RA Bill
Withhold against Unauthorizeed HSCs | 11200000 | Survey of the HSCs WIP,
Recovery due to already piad PA | -18881174 | Recovery fo the Already paid PA by the client |  | 1.88 | already ppaid Price adjsut
Recovery due to double payments | -25000000 | Due to the double payments by the client, this amount will be recovered |  | 2.5 | recovery double pmnt
Recovery due to 3rd EOT LD | -5433500 |  |  | 0.55 | 3rd EOT LD
Balance receivables | 178013056.6

## Bagalkot (hidden)
Name of Project |  | Bagalkot
Targeted Completion Date |  | 2024-03-15
PO Value |  | 52 cr
Gross Bill Till Date |  | 35.85 cr | Balance Receivable Amt 13 cr 16/12/23
SAP Billing |  | 37.83 cr
Project Manager |  | Purushotham Vijapur
Balance Days for Completion |  | 39
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date
2025-09-12 02:31
1 | Risining Main line- Valve Chambers | 0 | Nos | 39 | [6 empty] | Completed
2 | Linking work -200 mm DI to 200 mm MS | 0 | Nos | 39 | [6 empty] | Completed
3 | 6 nos Zone Commisining- Pipe line work | 422 | Mtr | 39 | 30 | [5 empty] | Shri Mukambika Builders Payment needs to be done
4 | 6 nos Zone Commisining- Valve Chambers | 0 | Nos | 39 | 0 | [5 empty] | Completed
5 | 6 nos Zone Commisining- Meter Fixing | 290 | Nos | 39 | 30 | [5 empty] | Shri Mukambika Builders Payment needs to be done
6 | 6 nos Zone Commisining- Meter refixing/HSC rectification | 500 | nos | 39 | 30 | [5 empty] | Shri Mukambika Builders Payment needs to be done
7 | SCADA Work |  | JOB | 39 | 30 | [5 empty] | Sai Applied technologies personnel should come and finish the balance works after Pontoon Installation
8 | Pontoon | 1 | NOs | 39 | 30 | [5 empty] | Procurement done erection pending due to 300 HP pumps
9 | Pontoon Pump Erection - 300 HP | 2 | Nos | 39 | 30 | [5 empty] | Procurement pending
10 | Electric Work for Pontoon Pump | 0 |  | 39 | 30 | [5 empty] | Transformer, and panels erected. connection from Panels to Pontoon pending. Will be done after pontoon erection.
Material Requirement
Sr No | Material | Qty | Unit | STO/PR/PO |  | Vendor | Status
LC payment
1 | Pontoon Pumps-300 HP | 2 | Nos |  |  | AQUA Pump | LC payment
2 | Flaoter | [5 empty] | Pipes Supplied
3 | MS Bend 45 Deg 300 mm | 1 |  |  |  |  | Supplied
4 | [6 empty] | Panel supplied
| Contractors | Man power | Particulars
1 | Shri Mukambika Builders | 15 | Pipeline, Road Restoration, Valve chambers, Thrust Blocks, HSCs, Meterfixing, Refiiting of HSCs , Rented Vehicles like Excavator, Tractor and tankers, TATA Ace
2 | Afroz Navaldar | 6 | Pipeline, Road Restoration, HSCs, Meterfixing
3 | Ravi Rajput | 8 | Meterfixing and Refitting
Balance amount pending from Department
Sl No | Particulars | Amount | Reasons
1 | RA Bill-20 | 10820618 | Awaiting EOT-4
2 | EIRL | 14906186.56 | Awaiting Variation proposal approval from SLTC, SHPSC authority
3 | GST reimbursement | 12407345 | New Guideline given bu Watr Board
4 | Workslip | 18473617.43 | Awaiting Variation proposal approval from SLTC, SHPSC authority
Total |  | 56607766.99
| pump | 10000000
66607766.99

## Bijapur (hidden)
Works | Engineer Incharge | Supervisiors | Balance Qty | Unit | 2023-11-23 |  |  |  | 2023-12-23 |  |  |  | Remarks | Requirement from HO | Requirement from Client
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Zone 7
Pipe Laying & Interlinkings | Basavraj G | Shashikant D | 0 | Mtrs | [8 empty] | commisioning of the zones can be done only after bulk water supply |  | Bulk water supply
HSCs |  |  | 0 | Nos
Water Trial |  |  | 1 | Job | bar: 2023-11-23 W3 to 2023-11-23 W4
Zone 14
Pipe Laying & Interlinkings | Ram T | Prasad J Ashok | 0 | Mtrs | [8 empty] | Completed and commisioned, Consumer Billing is also started
HSCs |  |  | 0 | Nos
Valve Fixing |  |  | 0 | Nos
Water Trial |  |  | 0 | Job
Zone 19
Pipe Laying & Interlinkings | Basavraj G | Javeed Shashikant Raghvendra | 0 | Mtrs | [8 empty] | Trial Run in progress | Labour Payments through Suprada Industries | Bulk water supply
HSCs |  |  | 0 | Nos
Valve Fixing |  |  | 0 | Nos
HSc Refitting |  |  | 500 | Nos | bar: 2023-11-23 W3 to 2023-11-23 W4
Water Trial |  |  | 1 | Job | bar: 2023-11-23 W3 to 2023-11-23 W4
Zone 11
Pipe Laying & Interlinkings | Ram T | Vishal M Mohmad Chetan | 200 | Mtrs | [8 empty] | Completed and commisioned, Consumer Billing is also started
HSCs |  |  | 0 | Nos
Valve Fixing |  |  | 0 | Nos
Water Trial |  |  | 0 | Job | bar: 2023-11-23 W3 to 2023-11-23 W4
Zone 21
Pipe Laying & Interlinkings | Santosh Pawar | Javeed Abhi Prakash | 0 | Mtrs | [8 empty] | Trial Run in progress | Labour Payments through Suprada Industries | Bulk water supply
HSCs |  |  | 0 | Nos | bar: 2023-11-23 W3
Valve Fixing |  |  | 0 | Nos | bar: 2023-11-23 W3 to 2023-11-23 W4
HSc refitting |  |  | 300 | Nos | bar: 2023-11-23 W3 to 2023-12-23 W2
Water Trial |  |  | 1 | Job | bar: 2023-11-23 W3 to 2023-12-23 W2
Zone 20
Pipe Laying & Interlinkings | Santosh Pawar | Javeed Abhi Shashikant | 20 | Nos | [8 empty] | commisioning of the zones can be done only after bulk water supply | Labour Payments through Suprada Industries | Bulk water supply | bar: 2023-11-23 W3 to 2023-12-23 W1
HSCs |  |  | 100 | Nos | bar: 2023-11-23 W3
Valve Fixing |  |  | 15 | Nos | bar: 2023-11-23 W3 to 2023-12-23 W1
Water Trial |  |  | 1 | Job | bar: 2023-11-23 W3 to 2023-12-23 W2
Zone 10
Pipe Laying & Interlinkings | Ram T | Vinayak Arun Parshuram Sanju Rathod | 0 | Mtrs | [8 empty] | Trial Run WIP | Labour Payments through Suprada Industries
HSCs |  |  | 50 | Nos | bar: 2023-11-23 W4
Valve Fixing |  |  | 5 | Nos | bar: 2023-11-23 W4
HSc refitting |  |  | 200 | Nos | bar: 2023-11-23 W4 to 2023-12-23 W1
Water Trial |  |  | 1 | Job | bar: 2023-11-23 W4 to 2023-12-23 W1
JM OHT
CI Pipe Leakage Rectification | Ram T | Javeed Abhi | 1 | Job | [8 empty] | All works are completed and water supply started from New OHT | For Finishing works, Payments from Suprada industries
Hydrotesting |  |  | 1 | Job
Arresting Leakages |  |  | 1 | Job
Fixing of MS Stairs, Gates |  |  | 1 | Job
Bed Concreting & Finishing |  |  | 1 | Job | bar: 2023-11-23 W4 to 2023-12-23 W1
Providing Fencing |  |  | 3 | Job | bar: 2023-11-23 W4 to 2023-12-23 W1
EMF Fixing
Completed Zones(2,3,4,5,9,16,18,22) |  |  | 8 | Nos | [8 empty] | Balance Valves to be fixed after the completion of all works | bar: 2023-11-23 W3 to 2023-12-23 W3
Under completion Zones(7,10,11,14,19,20,21) |  |  | 15 | Nos | bar: 2023-12-23 W2 to 2023-12-23 W4
PRV Fixing
Completed Zones(2,3,4,5,9,16,18,22) |  |  | 23 | Nos | [8 empty] | Balance Valves to be fixed after the completion of all works | WIP | NA | bar: 2023-11-23 W3 to 2023-12-23 W2
Under completion Zones(7,10,11,14,19,20,21) |  |  | 38 | Nos | bar: 2023-12-23 W2 to 2023-12-23 W4
PMP Fixing
Completed Zones(2,3,4,5,9,16,18,22) |  |  | 0 | Nos | [8 empty] | Completed | Completed | Completed
Under completion Zones(7,10,11,14,19,20,21) |  |  | 7 | Nos | [8 empty] | Completed
Valve chambers
Completed Zones(2,3,4,5,9,16,18,22) |  |  | 24 | Nos | [8 empty] | Balance Valves to be fixed after the completion of all works | WIP | bar: 2023-11-23 W3 to 2023-12-23 W4
Under completion Zones(7,10,11,14,19,20,21) |  |  | 49 | Nos | bar: 2023-12-23 W2 to 2023-12-23 W4
Survey of HSC | Rakesh Devar | Abu Bakar | 8000 | Nos | [9 empty] | WIP | bar: 2023-11-23 W3 to 2023-12-23 W4
Surface Box |  |  | 797 | Nos | [9 empty] | Labour Payments | bar: 2023-11-23 W3 to 2023-12-23 W4
Chlorine Room
Civil Work | Ram T | Ram T | 4 | Nos | [8 empty] | Completed | bar: 2023-11-23 W3 to 2023-12-23 W1
Finishing Works |  |  | 4 | Nos | [8 empty] | Completed | bar: 2023-11-23 W4 to 2023-12-23 W3
Electrical Works | Rakesh Devar | Rakesh Devar | 4 | Nos | [8 empty] | WIP | bar: 2023-11-23 W3 to 2023-12-23 W4
Chlorinators
Supply | Rakesh Devar | Rakesh Devar | 15 | Nos | [8 empty] | Supply pending from HO | bar: 2023-11-23 W4 to 2023-12-23 W2
Installation |  |  | 15 | Nos | bar: 2023-12-23 W2 to 2023-12-23 W4
SCADA
Level Indicator | Rakesh Devar | Rakesh Devar | 4 | Nos | [8 empty] | Site Clearence pending | bar: 2023-12-23 W2 to 2023-12-23 W4
Valve Accutators @ inlet |  |  | 22 | Nos | bar: 2023-11-23 W3 to 2023-12-23 W4
WTP SV |  |  | 72 | Nos | [8 empty] | Vendor finalization | bar: 2023-11-23 W3 to 2023-12-23 W4

## Bagalkot receivable (hidden)
Balance amount pending from Department |  |  |  | 13/12/23 | Amount we get after Bill cleared from Department
Sl No | Particulars | Amount | Reasons |  | Pipeline (Earth work, Pipe laying and jointing, Hydrotesting, Damage repairs, Parallel Lines, Rising main) | 4785479.54
1 | RA Bill-20 | 10820618 | Bill under preperation |  | Valves supply and installation | 431825
2 | EIRL | 15983211.7 | Awaiting Variation proposal approval from SLTC, SHPSC authority |  | HSCs | 1171102.28
3 | GST reimbursement | 12407345 | Going change as per KUWS&DB AE |  | Chlorine room | 904578.34
4 | Workslip | 20585238.24 | Awaiting Variation proposal approval from SLTC, SHPSC authority |  | CI Valve box and Valve chambers | 848432.21
5 | Commissioninig | -0.0006 | Bill Under Scrutiny |  | Road restoration(Pipeline and at WTP) | 28005820.97
[5 empty] | OHT | 1230262.04
Total |  | 59796412.94 |  |  | SCADA | 1396941.3
[5 empty] | Pumping machineries and Transformer (Finalised after Rakesh clarifies qty and specs with AE, Bagalkot) | 5035896
Balance amount from pending work |  |  |  |  | Total | 43810337.68
Sl No | Particulars | Amount | Reasons
1 | Pontoon | 24081236.36 | Procurement under progress |  | Commssioning amount we get after Bill cleared from Department
2 | 300HP Pump | 10009055.85 | Procurement under progress |  | Pipeline (Earth work, Pipe laying and jointing, Hydrotesting, Damage repairs, Parallel Lines, Rising main) | 1560396.13
[5 empty] | Valves supply and installation | 329583.05
Total |  | 34090292.21 |  |  | HSCs | 1300754.66 |  | 8.9
Chlorine room
[5 empty] | CI Valve box and Valve chambers | 58702.8
[5 empty] | Road restoration(Pipeline and at WTP) | 1947492.93
[5 empty] | OHT | 303914.55
SCADA
Pumping machineries and Transformer (Finalised after Rakesh clarifies qty and specs with AE, Bagalkot)
[5 empty] | Total | 5500844.12 | 0.55008
Amount we get after Variation proposal approval (EIRL)
[5 empty] | Pumps(15HP, 100HP and 10HP) and 355mm HDPE Pipes | 8843153.3
[5 empty] | Transformer | 816687.88
[5 empty] | 300mm DI Pipes, Sluice Valves and PCV | 5679045.07
[5 empty] | MDPE Pipes | 644325.45
[5 empty] | Total | 15983211.7 | 1.5983
[8 empty] | 1.59 | EIRL
[5 empty] | Amount we get after Variation proposal approval (Work slip) |  |  | 5.5 | Comm
[5 empty] | Pipeline (Earth work, Pipe laying and jointing, Hydrotesting, Damage repairs, Parallel Lines, Rising main) | 18814050.87 |  | 2.05 | Worl slip
Valves supply and installation
HSCs
Chlorine room
CI Valve box and Valve chambers
Road restoration(Pipeline and at WTP)
[5 empty] | OHT | 896450.62
SCADA
[5 empty] | Pumping machineries and Transformer (Finalised after Rakesh clarifies qty and specs with AE, Bagalkot) | 874736.7584
[5 empty] | Total | 20585238.25 | 2.0585
4.2069

## Jabalpur 1 (hidden)
Name of Project |  | Bagalkot
Targeted Completion Date |  | 2024-03-15
PO Value |  | 25.47 | Capex | 22.82 Cr | O&M 2.65 cr
Gross Bill Till Date |  | 14.18 Cr | Capex expected to Short close Rs 15 cr
SAP Billing |  | 14.88 Cr
Project Manager |  | Ajay Paliwal
Balance Days for Completion |  | #NAME?
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date
2025-09-12 02:31
| Pipe Laying-Ahinsha chowk 90 mm Road Cross | 1 nos |  | 28 | 2 | After site clearance will completed. |  |  |  | Site is still not clear
| Pipe Laying-Ranital to Petrol pump-200 mm | 125 Mtr |  | 28 | 10 | After site clearance will completed. |  |  |  | Site is not clear due to flyover work goning
| Pipe Laying-Karmachand Chouk- CC Road Cross- 90 mm | 20 mtr |  | 28 | 8 | After site clearance will completed. |  |  |  | Site is still not clear due to deance Market area.
| Pipe Laying-Karmachand Chouk- 90 mm | 30 mtr |  | 28 | 8 | After site clearance will completed. |  |  |  | Site is still not clear due to deance Market area.
| Pipe Laying-Ranital Road- 90 mm | 140 mtr |  | 28 | 10 | After site clearance will completed. |  |  |  | Site is not clear due to flyover work goning
| Pipe Laying- Pragaya colony near Navin Vidya bhavan.-CC road-180 mm | 62 mtr |  | 28 | 4 | After site clearance will completed. |  |  |  | Pepoles are not allowing to break new double CC road.
| Pipe Laying- Pragaya colony near Navin Vidya bhavan.-CC road-90 mm | 62 mtr |  | 28 | 6 | After site clearance will completed. |  |  |  | Pepoles are not allowing to break new double CC road.
| Pipe Laying- Pragaya colony near Navin Vidya bhavan.-CC road-110 mm | 113 Mtr |  | 28 | 6 | After site clearance will completed. |  |  |  | Pepoles are not allowing to break new double CC road.
| Pipe Laying- In front of Brand factory, Shastri bridge- 200 mm- HDD work | 88 mtr |  | 28 | 20 | After site clearance will completed. |  |  |  | No site clearance from client. Electrical cables | Sarching HDD M/c in Jabalpur.
| Pipe laying- In front of Bhawartal Garden near Church -110 mm | 87 mtr |  | 28 | 3 | After site clearance will completed. |  |  |  | Both side paver block
| Pipe laying- Jabalpur hospital Road gali- 110 mm- Total CC | 99 mtr |  | 28 | 8 | After site clearance will completed. |  |  |  | Resident wants to connect with exising line.
| Junction Connection-Ranital chowk-200 /90 mm | 5 mtr |  | 28 | [5 empty] | completed.
| Junction Connection-Karamchand chowk-200 mm | 25 mtr |  | 28 | [5 empty] | completed.
| Junction Connection-Sai Mandir gali, Model road-110 mm | 3 mtr |  | 28 | 2 | After site clearance will completed. |  |  |  | No site clearance due to drain, boundary valve and shops.
| Junction Connection-Jabalpur hospital Road gali-110 mm | 2 mtr |  | 28 | [5 empty] | completed.
| Junction Connection-Nagar Nigam market, Naudra bridge- 90 mm | 3mtr |  | 28 | [5 empty] | completed.
| Hydraulic Valve Erection- 600 mm Inlet Hydraulic valve Chanchala bai OHT | 1 nos |  | 28 | 15 |  |  |  |  | completed. | Visit of Talis hydraulic valve servies person.
| Isolation Valve -200 m Beside Shastri Bridge | 1 nos |  | 28 | [5 empty] | completed.
| Hydraulic valve-Inlet/Outlet Hydraulic valve Bhawartal OHT-400 mm & 600 mm | 2 nos |  | 28 | 15 |  |  |  |  | Erection completed and commissioning balance. | Visit of Talis hydraulic valve servies person.
| Automation- Chanchala Bai OHT- ULT, EMFT, PLC Panel, Try laying, Cable laying and Earthing work completed. | JOB |  | 28 | [5 empty] | Erection completed.
| Automation- RTU, PT and Solar panel erection balance. | JOB |  | 28 | [5 empty] | Erection completed.
| HSC- | 469 nos |  | 28 |  | In progress
| AMR Meter with box | 2110 Nos |  | 28 |  | In progress |  |  |  | Awiting Meter box cover. | Meter Box from AIVA pending from HO.
| Chanber Work-OHT side and DMA Hydraulic valve. | 16 nos |  | 28 | 15 | In progress
Material Requirement
Sr No | Material | Qty | Unit | STO/PR/PO |  | Vendor | Status
1 | Water Meter Box | 2300 | Nos |  |  | AIVA Engg,Pune | LC payment

## Balaghat (hidden)
Project |  | Balaghat
Targeted Completion Date |  | 2023-12-31
PO Value |  | 38.68Cr | Capex | 38.68Cr
Gross Bill Till Date |  | 36.55 Cr
SAP Billing |  | 38.93 Cr
Project Manager |  | A B Paliwal
Balance Days for Completion |  | #NAME?
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date
2025-09-12 02:31
1 | Out of 6 Zone in 5 nos Zone, somepart is having Low Pressure and Water not reaching problems |  |  | #NAME? |  | Idetified part valve Managemeent, Blockage removal, leakage reapir work is in process | 2 supervisors, 10 labours |  |  | Open connection wthout tap, Localized pumping and intermittant supply is creating low pressure problems | One Welder
2 | New HSC | 100 | Nos |  |  | In progress
Material Requirement
Sr No | Material | Qty | Unit | STO/PR/PO |  | Vendor | Status
1
Balaghat receivable
| PIPE & HSC BILLING AMOUNT | 11843782.6
| DAMAGE PIPE REPAIR WORK BILLING | 1400000
| 5% SD AMOUNT PENDING WITH MUNICIPAL | 17257177
| HOLD AMOUNT FOR ROAD RESTROTION | 400000
| 10% AMOUNT E.E INSPECTION | 2676992.59
| 3% SD AMOUNT R A BILL NO 3 DT 20/12/2017 | 254263
| TOTAL AMOUNT | 33832215.19

## Jabalpur (hidden)
Balance work status sheet
SR. NO. | DESCRIPTIONS | LOCTIONS | REMARKS | Length | Dia | Time Period | CC | Status
1 | Pipe line laying (250,200,180,110mm) | Yatayat chowk police Thana side. | No site clearance from client. Paver block issue, cables and inlet line of Chanchlabai OHT. | 47 Mtr. | 250mm | 2 Days |  | Completed
|  | Ahinsha chowk | Site clear but main market. | 60 Mtr. | 180mm | 1 Day | 8 Mtr. CC | Completed
|  | Ahinsha chowk to Nala Jamadar road | CC, boundary wall issue and drain crossing | 88mtr. | 110mm |  | 40 mtr CC | Completed
|  | Ahinsha chowk | No layout from department due market area. | 50 mtr. | 90mm | 2 Day |  |  | Road Crossing pending
|  | Ranital to Petrol pump | No site clearance due to flyover work going on.( drain and boundary wall issue) | 150 MTR. | 200 mm | 4 Days |  | Road crossing completed | Balance work of 125M.
|  | Russell chowk to Marble hospital fencing | Drain and cable hindrances, main market. | 102mtr | 110mm | 2 Days | 45mtr, drain crossing 6mtr. | Completed
|  | Karmchand chowk | No layout from department due market area. | 114mtr. | 90mm | 2 Days | 20 mtr CC, road crossing |  | Pending
|  | Karmchand chowk | No layout from department due market area. | 30mtr. | 90mm | 2 Days |  |  | Pending
|  | Jaynti complex, civic centre | Drain crossing. | 4 mtr. | 140mm | 1 Day |  | Completed
|  | Ranital road | No site clearance due to drain & boundary wall issue. | 140 mtr. | 90mm | 2 Days |  |  | Pending
|  | Madan Mahal Thana to Mayur hotel road | No site clearance due to flyover work going on. | 100mtr. | 110mm | 2 Days |  | Completed
|  | Madan Mahal Thana to NMT | No site clearance due to flyover work going on. | 100mtr. | 180mm | 2 Days |  | Completed
|  | Kotak Mahindra bank chowk | No site clearance due to drain crossing,Transformer & CSS issue.. | 8mtr. | 280mm | 1 Day |  | Completed
|  | Pragaya colony near Navin Vidya bhavan. | Double CC new road issue | 62mtr. | 180mm | 3 Days | Total CC |  | Pending
|  | Pragaya colony near Navin Vidya bhavan. | Double CC new road issue | 62mtr. | 90mm | 3 Days | Total CC |  | Pending
|  | Pragaya colony lane near Navin Vidya bhavan. | CC issue | 113mtr | 110mm | 4 Days | Total CC |  | Pending
|  | MLB chowk to Hot chips | Pipe line to be laid or not finalized by JSCL. | 300mtr | 90mm | 7 Days |  | Completed
|  | Shastri bridge to old bus stand | No site clearance due to drain, boundary valve and shops. | 300mtr | 90mm | 7 Days | HDD work | Completed
|  | BSNL office to Yatayat chowk | Due to BSNL cables network | 100mtr. | 90mm | 3 Days | 43 mtr CC | Completed
|  | In front of Brand factory, Shastri bridge | No site clearance from client. Electrical cables | 88mtr. | 200mm |  | HDD work |  | Pending
|  | In front of Bhawartal Garden near Church | Both side paver block | 87mtr. | 110mm | 2 Days | 6 mtr. CC |  | Pending
|  | Jabalpur hospital Road gali | Resident wants to connect with exising line. | 99 mtr | 110mm |  | Total CC |  | Pending
|  | Beside Shastri Bridge gali | Paver block and drain crossing | 180mtr | 110mm | 2 Days | 30 mtr CC | Completed
|  | Jabalpur hospital opp. Road | Hurdle due to Private property. | 150mtr. | 90mm | 3 Days
2 | Junction work | Madan Mahal Thana | No site clearance due to flyover work going on. | 25mtr. | 200mm | 2 Days |  | Completed
|  | Bombay hospital chowk | CSS Panel installed by contractor | 5mtr. | 280/160mm | 1 Day |  | Completed
|  | Kotak Mahindra bank chowk | Drain & Cable. | 15mtr. | 280/140mm | 2 days |  | Completed
|  | Ranital chowk | Flyover work going on. | 5mtr. | 200/90mm | 1 Day |  |  | Pending
|  | Karmchand chowk | Electric transformer and cables | 25 mtr. | 200mm | 1 Day |  |  | Pending
|  | Sai Mandir gali, Model road | No site clearance due to drain, boundary valve and shops. | 3mtr | 110mm | 1 Day |  |  | Pending
|  | Jabalpur hospital Road gali | Resident wants to connect with existing pipe line | 2mtr | 110mm | 1 Day |  |  | Pending
|  | Nagar Nigam market, Naudra bridge |  | 3 mtr. | 90mm | 1 Day |  |  | Pending
3 | Hydraulic/Isolation valve erection work | NMT, Dr. Lele line(225mm line) |  |  | 200mm | 2 days |  | Completed
|  | NMT, Amrish Misrha line 180mm line | Flyover work going on. |  | 150mm | 1 Day |  | Completed
|  | Sai Mandir road, 200mm | Need to be shut down water supply line |  | 200mm |  |  | Completed
|  | Inlet Hydraulic valve Chanchala bai OHT | Shutdown yet not to be provided from client. |  | 600mm |  |  |  | Pending
|  | Isolation valve on model road 225mm line | Vakil House, Near yatayat chowk |  | 200mm | 1 Day |  | Completed
|  | Isolation valve 225mm line | Beside Shastri bridge |  | 200mm | 1 Day |  |  | Pending
|  | Isolation valve 110mm line | Yes Bank, |  | 100mm | 1 Day |  | Completed
|  | Isolation valve 225mm line | Old bus stand |  | 200mm | 1 Day |  | Completed
|  | Isolation valve 225mm line | Car Bazar, Near Abhinanadan hotel |  | 200mm | 1 Day |  | Completed
|  | Isolation valve 315mm line | Shashtri Bridge |  | 300mm | 1 Day |  | Completed
|  | Isolation valve 180 mm line | Teen Patti, in front of Nagar Nigam |  | 150mm | 1 Day |  | Completed
|  | Isolation valve 200 mm line | Chanchalabai OHT chowk |  | 200mm |  |  | Completed
|  | Inlet/Outlet Hydraulic valve Bhawartal OHT | 450mm outlet yet not to be provided from client. |  | 600/400mm |  |  |  | Pending
4 | Automation work | Chanchala Bai OHT
|  | ULT, EMFT, PLC Panel, Try laying, Cable laying and Earthing work completed. | ogress |  |  | 2 days | After all Hydraulic valve erection and site clearance |  | Pending
Bhawartal OHT
|  | PLC Panel erection work completed. | PT, ULT, EMFT, Try laying, Cable laying and Earthing balance. |  |  | 3 days |  | Completed
DMA
|  | Hydraulic valve erected. | RTU, PT and Solar panel erection balance. |  |  | 4 days |  |  | Pending
5 | HSC connections |  | 469 balance. |  |  |  | Work in progress | Work in progress
6 | Smart Meter with box |  | 2110 balance. |  |  |  | Work in progress |  | Box still pending
7 | Chamber work | OHT side and DMA Hydraulic valve. | work in progress ( 3/13 nos HV) |  |  |  | Work in progress | Under progress

## Gokak (hidden)
Ch Dadri |  | Gokak
Completion Date- O& M |  | 2024-03-31
PO Value |  | 27.90 Cr | Capex | 21.45 cr | O&M | 6.45 Cr
Gross Bill Till Date |  | 25.25 Cr
SAP Billing |  | 26.98 cr |  | O/ Normal- 3.14 Cr
Project Manager |  | Lokesh Sanadi
Balance Days for Completion |  | #NAME? | Last Quarter O &M in Process
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date
2025-09-12 02:31
1 | O&M Handing Over by 31st March 24 |  |  | #NAME? | [5 empty] | Excrow Account yet not transfer fm KUIDFC to CMC
| Receiavble as on | 2025-09-12 02:31
| Receivable | in Lakh |  |  |  | Rev receivable
| Final Bill | 3 |  |  |  | 0.76
| 16 & 17th ,18 ,19 Q - O&M charges | 140 |  |  |  | 140
| last quarter 20th | 30 |  |  |  | 30
| O&M Works | 50 |  |  |  | 50
| Flood Damge Works | 150 |  |  |  | 150
| Total | 373 |  |  | 4.32 | 370.76

## Nipani (hidden)
Ch Dadri |  | Nipani
Completion Date- O& M |  | 2025-03-31
PO Value |  | 29.9 Cr | Capex | 23.52 | O&M 6.38Cr
Gross Bill Till Date |  | 24.96 Cr
SAP Billing |  | 26.75 Cr |  | O/ Normal-
Project Manager |  | Laxmikant Shellagi
Balance Days for Completion |  | #NAME?
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date
2025-09-12 02:31
1 | O&M Handing Over by 31st March 25 |  |  | #NAME?
| Receiavble as on | 2025-09-12 02:31
| Receivable | in Lakh
| Final Bill | 40
48
| 11 to 14 th Q uarter O&M | 140
| 15 to 20 th Quarter | 220 |  |  | 228 |  | onm | Till 10thQ | 2046017 | Gross incl GST recd
| O&M works | 30 |  |  | 136
| Total | 430 | [5 empty] | 5.68
Total

## Nipani receivable 6th Feb 24 (hidden)
Nippani Project Bills submitted and pending bills details
Slno | Perticular | Period | Amount | Remarks
1 | RA 24 & Final | Phase I | 6423609.71 | Bills Submitted to HO, Payment yet to be made,
| 6th to 10th Qtrly bills | July -2021 to Sept-2022
2 | 11th Qtrly bill | Oct-2023 to Dec-2023 | 4000000 | Bills Submitted to HO, Payment yet to be made, (Including fixed & performance)
3 | 12th Qtrly bill | Jan-2023 to Mar-2023 | 4000000
4 | Desil & oil supplied bills, WTP & Bhangi chall DG Diesel supplied and Jackwell oil supplied for pumps. |  | 478000 | Bill Submitted to HO, Payment to be made,
6 | 13th Qtrly bill | April-2023 to June-2023 | 3750000 | Bills Submitted to HO, Payment yet to be made, (Including fixed & performance)
7 | 14th Qtrly bill | July-2023 to Sept-2023 | 3750000
5 | Additional HSC under BOQ (125% rate) | BOQ extra | 2000000 | Submitted to Division office
| 15th Qtrly bill | Oct-2023 to Dec-2023 | 3750000 | Prepration Under progress
8 | O&M (Extra works) Pipe laying and HSC | O&M period | 10752820.81 | Bill is ready to submit
9 | O&M Extra works leakage rectification & Customer care center | O&M period | 2000000 | Bill preparation under progress
10 | WTP to MBR 450mm leakage rectification work done | O&M period | 500000 | Bill preparation under progress
41404430.52
1.48
5.48

## Bijapur 1 (hidden)
Name of Project |  | Bijapur
Targeted Completion Date |  | 2024-03-15
PO Value |  | 204.79 Cr | Capex | 174 Cr | O&M | 27.79
Gross Bill Till Date |  | 141.32 Cr | Balance Receivable Amt 25 Cr
SAP Billing |  | 174.98 Cr
Project Manager |  | Ram Toshniwal
Expected Capex closing |  | 158.82 Cr
Balance Days for Completion |  | 45
| Status as on | 2025-09-12
Sr No | Item/Activity | Balance Qty for Completion/ Handover | Unit | Balance Days for Target Completion | Expected Days for Completion | Planning For Completion | Resources Alloted for Completion | Present Out put/Day | Required Output/Day | Issue/ Hindrances | Resources Required | Balance qty as on date
2025-09-12 02:31
| Zone Trail Run /Commissioning Zone 19 | completed- |  |  |  | Trial Completed | Engg- Basavraj - Suprv-Javeed Shashikant Raghvendra |  |  | Due to Summer, Bulk Shortage. Partial Supply through our network and remaining PVC | Labour Payment fm Suprada
| Zone Trail Run /Commissioning Zone 21 | completed- |  |  |  | Trial Completed | Engg- Santosh Pawar- Supvr-Javeed Abhi Prakash |  |  | Due to Summer, Bulk Shortage. Partial Supply through our network and remaining PVC | Labour Payment fm Suprada
| Zone Trail Run /Commissioning Zone 20 | Trial Run in Process |  | Balance Qty for Completion/ Handover |  |  | Engg- Santosh Pawar- Supvr-Javeed Abhi Shashikant |  |  | Due to Summer, Bulk Shortage. Partial Supply through our network and remaining PVC | Labour Payment fm Suprada
| HSC Refitting- Zone 19 | 200 Nos | [7 empty] | HSC can be refiited after the supply through our nrtwork
| HSC Refitting- Zone 21 | 300 Nos |  | COmpleted- | [5 empty] | HSC can be refiited after the supply through our nrtwork
| HSC - Zone 20 | 100 nos |  | completed-
| HSC Refitting- Zone 10 | 200 nos |  | completed- | [5 empty] | Completed
| HSC - Zone 10 | 50 nos |  | Trial Run in Process | [5 empty] | Completed
| Pipe Laying & Interlinkings-Zone 20 | 20 nos |  | #REF! | [5 empty] | Completed
| Pipe Laying & Interlinkings-Zone 11 | 200 mtr laying | [7 empty] | Completed
| JM OHT- Bed Concrete,Finishing, Fencing | JOB |  |  |  |  | Engg Ram |  |  | Completed
| EMF Fixing -Completed Zones(2,3,4,5,9,16,18,22) | 8 nos |  | 100 nos | [5 empty] | Completed
| EMF Fixing- Under completion Zones(7,10,11,14,19,20,21) | 15 nos |  | 200 nos | [5 empty] | WIP
| PRV Fixing- Completed Zones(2,3,4,5,9,16,18,22) | 23 nos |  | 50 nos | [5 empty] | WIP
| Valve Fixing Zone 20 | 15 Nos |  | 20 nos | [5 empty] | Completed
| Valve Fixing Zone 05 | 5 nos |  | 200 mtr laying | [5 empty] | Completed
| Valve Chamber-Completed Zones(2,3,4,5,9,16,18,22) | 24 nos |  | JOB | [5 empty] | Completed
| Vave Chamber- Under completion Zones(7,10,11,14,19,20,21) | 49 Nos |  | 8 nos | [5 empty] | WIP
| Survey of HSC | 8000 Nos |  | 15 nos |  |  | Rakesh Devar, Abu Bakar |  |  | WIP, 1500 Legalized by department
| Fixing of Surface Box | 797 Nos |  | 23 nos | [6 empty] | Labour Payment fm Suprada
| Chlorine Room-Electric Works | 4 nos |  | 15 Nos |  |  | Rakesh Devar
| Chlorinator-Suply &Installation | 15 nos |  | 5 nos |  |  | Rakesh Devar
| SCADA-Level Indicator | 4 nos |  | 24 nos | [5 empty] | site clearance pending
| SCADA-Valve Accutators @ inlet | 22 nos |  | 49 Nos | [5 empty] | site clearance pending
| SCADA-WTP Valves | 62 nos |  | 8000 Nos | [5 empty] | WIP
| Enter into O&M Phase |  |  |  | JAN End
Material Requirement
Sr No | Material | Qty | Unit | STO/PR/PO |  | Vendor | Status
1 | Chlorinator | 15 | Nos |  |  | Group Industries | Material ready, LC to be given
2 | Water Meter | 3000 | Nos |  |  | Pune | PO raised
| Contractors | Man power | Particulars
Balance amount pending from Department
Sl No | Particulars | Amount | Reasons
Total |  | 0